## Slide 1: Event Management Course and Workshop
For Triathlon Local Organizing Committees (LOCs)
Facilitators: Terry Hooper & Marlene Hooper
Notes: 1

## Slide 2: Course Abstract
Goals
  To increase the knowledge, skills, and capabilities of the individuals and groups involved in managing events.
  To plan, organize, and produce safe, successful events that meet stakeholder needs.
Target
  Community Level, Volunteer Event Organizers Sanctioned by Triathlon Provincial Sport Organization (PSO)
In Scope
  Triathlon PSOs: Alberta, British Columbia, Saskatchewan
  Indoor and Outdoor Swim Events
Attendee Prerequisites
  Event Organizing Experience: None to Moderate
  PTO 1 and 2 ‘Trained’ Status (Preferred)

## Slide 3: Course Content Sources
Triathlon Alberta
Triathlon BC
World Triathlon
Personal Experience

## Slide 4: Course Sessions
Format
  Recorded Video Followed By Live Workshop
Session 1: Setting the Stage
  Expectations and Roles of Various ‘Actors’
Sessions 2 – 4: Writing the Event Script
  Pre-Event, Event Days, Post-Event
  Tasks, Timelines, Checklists
  Address All Actors’ Wants, Needs, Expectations
  Sample Templates and Examples

## Slide 5: Writing the Event Script
Act 1: Ten to Five Months Prior
Act 2: Four Months to One Week Prior
Act 3: Event Week, Day(s) of Event, and Post Event
*The items discussed will be provided in a checklist

## Slide 6: Four Months Prior
Final Registration Pre-Opening Considerations
Open Online Registration
Local Media Advertising and Articles
Arrange Meetings with Technical Delegate
Notes: Final Registration Pre-Opening Considerations
  Information the registrant should have collected and ready before starting (e.g., pool swim time, membership number).
  Event date, time, and location.
    For confirmation of event dates allowance, use scheduling estimator *example with template*
  Link to web site page about event.
    High level event schedule including pre-event activities.
      Include mention if an AG/Elite briefing will be given. Confirm collaboration and involvement with TD.
    What’s included (e.g., lunch, package pickup swag).
    General rules.
      Open water swim wetsuit cutoff information.
      Can link to PSO/WT rules.
    General maps.
    Accommodations.
    Qualifier events and info about Expressions of Interest.
    Draft-legal vs not.
    Outline cancellation policy.
      New consideration is air quality: https://www.trisask.org/wp-content/uploads/Tri-Sask-AQHI-Policy-2023-2023-08-01-Final-Draft-Clean.pdf
      Awareness of budget fixed vs variable costs and revenues should help understand impact of cancellation. Consider options for return/carryover of fees and sponsorship funding.
  Categories with age restrictions, distances, cutoff times, and fees.
    https://www.tribc.org/wp-content/uploads/2023/02/PSO-Rules-APPENDIX-X-2023-booklet-Final-2.pdf
    Embed information within registration category descriptions with distances and whether draft-legal.
    Confirm age calculation date of registration software (should be December 31 of event year).
  All fees to expect (race, affiliation (e.g., PSO, National membership fees), processing fees (if paid by registrant).
    Connect to PSO/Tri Can membership registration.
  Team registrations and category restrictions.
  Link to cancellation policy.
  Have online registration approved if necessary (may take 2 or 3 business days).
Open Registration
  Each event may want this opened sooner depending on competing events that might capture participants early and poach them.
  Announce on all event’s communication channels: web site, Facebook, Twitter, Instagram, posters. Consider purchasing advertising on Facebook, and posting on triathlon club Facebook pages.
Local Media Advertising and Articles.
  Local newspapers often look for local stories. Often if there are advertising spots purchased, it can be tied to an article. If the event is non-profit, that can result in better rates.
    Determine if a deal can be struck to commit to several ads with articles – including a post-event article on results and thanks to sponsors. A title or higher-end sponsor may help fund this (the media outlet may also sponsor some of this).
  Tie articles together with web site information about general training plans and local training opportunities to encourage participants to take the plunge.
  Local radio and TV stations may offer spots on programs to interview about the event.
Arrange Meetings with Technical Delegate
  Determine a meeting schedule with Technical Delegate (if Head Referee is involved, the TD will invite them).
  The TD can be a valuable resource to double check and ensure various event needs have been addressed. Will refer to the World Triathlon Competition Rules, Provincial Rules, and Event Organizer’s Guide – plus personal experience from other events provincially, nationally, and internationally.
  Work with TD to cover off outstanding sanctioning needs and pre-event tasks, and schedule when items are to be addressed.

## Slide 7: Four Months Prior
Finalize Traffic Control Service’s Plans/Drawings
Submit Formal Roads and Highways Permits
Request Police Volunteers
Arrange for Bike Course Motos
Participants’ Swag and Race Items
Book Cargo Transportation
Arrange Announcer
Book Backup Power Generator
Notes: Finalize traffic control service’s traffic control plans.
  Will have been booked with budget that includes personnel, for given length of time, perhaps with weekend overtime, and any road equipment and transport.
  Should also have traffic control plan already drawn up to share with the road and highways agencies for permits.
Submit formal roads and highways permits with municipal and province.
  These agencies should have been contacted six months prior to ‘pencil in’ your event. This task is to formalize that commitment.
  Online submission and approval can take weeks.
Request Police volunteers
  RCMP and local police may offer support or have retired members/officers willing to step up.
Arrange for bike course motos for officials
  Talk to the TD. If there is a technical official designated for the bike course, they’ll need a quieter motorcycle with passenger seating with backrest and an extra helmet. Technical Officials can work with your Bike Captain and moto crew to provide instructions and information.
Participants’ Swag and Race Items
  Finalize sourcing of participants’ swag (t-shirts, bibs, swim caps, bike numbers, tattoos, wristbands, trophies, podium medals, participation medals).
    If wristbands are used for venue and food access for volunteers, ensure additional are ordered to cover those needs.
  Open orders with sources where necessary
  Should already know the suppliers and expected costs if quotes have been received for budgeting.
Book cargo transportation.
  Used to move equipment from suppliers to race site.
  E.g., U-Haul.
Arrange for announcer
  Key person to add colour, ambience, and information to the event, participants, and spectators.
  Book PA system. Consider sources like donations, rental companies, or music stores (e.g., Long and McQuade).Book backup power generator.
  If there is a power outlet source, great! But you should have a backup in case it goes down. Will be needed by PA, timing (for laptops), blow-up finish arch.
  May be able to get from rental company as a sponsorship in-kind donation.

## Slide 8: Three Months Prior
Produce Detailed Area Plans with Maps
Create and Order Course Signs
Road Hazards/Repairs Check
Confirm Swim Facilities
Participation Medals and Awards
Arrange Photography
Arrange Bike Mechanic
Notes: Produce Detailed Area Plans with Maps
  Work with and confirm with TD.
  General overview plan showing major areas on venue.
  Venue plan: participant/volunteer check in, medical, recovery area, food catering and distribution (participants and volunteers), timing tent, announcer area.
    Includes Finish plan: chute and corral access controls, gantry, finisher awards materials area, finish water area. May need iced towels or emergency warmup blankets depending on weather.
  Marine plan: warmup area, start area (AG in-water; Elite from start platform on water’s edge), distance layouts, buoys (with plan to set course day before event), volunteers (on kayaks/SUPs), boats with medical (for extraction) and Technical Official and marine patrol (if necessary), extraction location with access to and coordination with emergency transport, glasses table on exit.
    Arrange lifeguards based on expected numbers (1 per 50 participants in water).
    Watercraft movement plan.
    Emergency plan, contingency plan, swimmer audit plan.
  Transition plan: toilet access, relay process and locations, flow fairness routing, rack setup (with grouping by category and/or racer numbers), bikes/rack, and spacing between racks and between outside fencing controls.
    Determine entry/exit openings and controls.
    Mount/dismount area and line. Ensure marking is provided by either TOs or LOC (e.g., green/red duck tape for mount/dismount).
    Elite transition to have rack bins and appropriate rack spacing, nameplates.
  Bike/road plan: volunteer positions, turnaround signage (especially for staggered turnarounds), penalty box location (for Age Group). Aid stations for mid- and long-distance. Road equipment and locations (barricades, barrels, pylons, tall boys, event signs). If full or partial closures of roads: alternate traffic flow plans.
  Run plan: Determine locations and signage for turnarounds, distance markers, separation pylons, signage, penalty tent including upcoming tent notification sign and penalty notice board (for elite/U23/Junior), aid station(s).
  Timing plan: Locations and timing point flow plan for various events (e.g., triathlon vs. duathlon).
  Medical plan: Designation of lead medical contact. Location of medical and first responder personnel on different parts of course. Emergency vehicle movement and routing. Confirm communications between LOC and medical. Consider notifying local hospital of event.
  Communication plan:
  Contingency plans: weather (lightning, high winds, cold, hot), air quality, water quality and safety,
  *Examples from EOM*
  All go into Organizer’s Guide.
Create and order course signs
  Takes time and is expensive. Consider creating generic mounting boards with Velcro, and add components as needed with Velcro.
  Can add other indicators such as matching wristband colours for distances.
  Check in: Desk, pointer to transition and swim
  Swim: Staging Corrals, Swim Exit. Swim Start or event feather flags. For Elite-type beach start, start number platform.
  Transition: Swim In, Bike Out, Bike In, Run Out, Mount, Dismount.
  Duathlon Start
  Bike: Turnarounds with distances. Bike Penalty box 200m and for penalty box itself. Mid and Long Distance events would add Aid Station.
  Run: Turnarounds with distances. Distance markers. Aid Station Start/End Litter zones. Elite-type race: Run Penalty Box 200m, Penalty Box, perhaps a penalty board (as opposed to whiteboard in rain).
  Finish: Penalty board. Elite-type race: Athletes’ Lounge.
  “Event in Progress” caution signs if not already provided.
Check for road for issues, hazards, and necessary repairs
  On bike course: Look for potholes, cracks, sewer grates, street parking, construction (municipal and private), railway crossings, uncontrolled intersections, controlled intersections.
  On run course: ensure footing hazards are identified with remediation plan.
  Determine contact for patching any pertinent areas of risk on bike and run course.
  Determine potential conflicts with other events and businesses. Communicate the event usage of roads with the understanding that approval has been received from the authorities to use roads for event.
Confirm swim facilities
  For pool
    Follow up with earlier facility booking. Note that there will be a contract that outlines costs and lifeguard support requirements.
    Confirm staging and movement of swim start waves through facility.
    Ensure pool deck usage and access has been determined.
    Will want chairs for lap counters and kickboards for signaling last laps.
    Ensure egress to transition is available.
  For open water.
    Starting corral area, path from swim exit to transition.
    Arrange water quality testing.
    Determine if there is boat traffic concerns (e.g., fishing derbies with ramp close by, water recreational businesses).
    Beach and shallow water concerns (e.g., entry/exit with rocks, broken glass, fishing hooks).
      On lakes there shouldn’t be tidal concerns, but there may be water level issues depending on in/outflow controls and seasonal changes.
    Ensure weeds are controlled.
Arrange for participation medals and awards.
  These should have been budgeted with known supplier.
  Order them to ensure delivery in time.
  Consider ranking medals (gold, silver, bronze) for age groups, gender, Elite categories. PSO rules state they are not given out to racers under 12.
  Participation awards should be expected.
Arrange photography.
  Consider contacting local camera clubs.
  Request access rights to load resulting photos onto event’s online site (with acknowledgement to the photographers or club).
Arrange bike mechanic
  Sponsor in kind would be available on-site during transition open and through day.
  Standard articles with ability to take payment (e.g., tubes, helmets, chains, derailleur parts, etc.) along with sufficient bike pumps and tools.
  If you have previous-day check in, arrange for that day as well.
  This should be coordinated with any issues arising out of bike checks.

## Slide 9: Two Months Prior
Confirm Medical
Confirm Security
Final Ordering of Race Items
Confirm Inventory of Race Equipment
Create an Event Schedule
Update Organizer’s Guide
Event Reminders
Notes: Confirm Medical
  Contact name, phone number, email.
  Arrival time, size and type of support (including coverage of venue, bike, run, and evac).
  Ambulance on site.
  Swim safety personnel: lifeguards, search and rescue.
Confirm Security
  Arrival and departure times.
  For overnight equipment setup and especially if bikes are checked in day before.
Final Ordering of Race Items
  Clothing amounts with sizing will be submitted through vendor along with finalizing graphics to be applied.
  Cutoff for guarantee of clothing with requested sizing.
Confirm Inventory of Race Equipment
  Start horn, start platform, rangefinder (working?), buoys (with inflators), rope/anchors, bike racks, transition fencing, tables/chairs (checkin, recovery food/drink, aid stations, penalty tent, swim exit for glasses, awards, announcer, timing), water jugs with dispensers and cups (aid and finish), tents with anchors (penalty, announcer, timing), finish arch, radio system (and working), power extension cords, volunteer hi-vis vests, stop/slow signs, mount/dismount tape, and general office supplies. If part of base race equipment: PA system, Elite-type transition bins. And pylons, pylons, pylons!
  Course signage from past years’ event.
Create an Event Schedule
  Details what happens when, and who is responsible.
  Used to keep track that the event activities leading into the event days are being done and kept on track.
Update Organizer’s Guide
  All information should be compiled and documented in one Guide.
  Used as a basis for Volunteers’ Guide, Athletes’ Guide, and Captains’ Guide.
  Will continue to be updated, but take the time now to put everything known at this point in a document.
Event Reminders
  Participants: Remind that registration is open, clarify registration close date, any early-bird deadlines, and how to register. If there are capacity limits, provide information on those closed to registration, wait list options, or those close to closing.
  Volunteers: Remind about event,
  For the above, use tagging to separate those that have already registered as either participant and/or volunteer.
    Send separate communication to those registered to remind them of upcoming event’s activity schedule and information.

## Slide 10: One Month Prior
Certificate of Insurance Distribution
Publish Final Volunteer Guide
Compile Volunteer Lists
Schedule and Conduct Captains’ Meetings
Finalize and Confirm Venue Setup Needs
Create and Print Site Maps
Notes: Certificate of Insurance Distribution
  Often from PSO through their insurance provider.
  Names parties added where required: title and names sponsors, municipal and provincial organizations
Publish Final Volunteer Guide
  Provide all information any volunteers may be wanting to know before committing, or to have some confidence in participating in their role.
  Publish online so it can be referred to for any future Volunteer communications.
Compile Volunteer Lists
  Allocate volunteers to positions and send out reminder communications. Expect to receive cancellations.
  Have allocation ready to inform Captains of their area’s volunteer status.
  Determine areas that are missing required volunteers, and issue a general call for assistance to volunteer list and participants.
Schedule and Conduct Captains’ Meetings
  Update the event’s Organizer’s Guide and distribute prior to meeting.
  Gather all area Captains’ and review the general event information and their area’s specifics (as outlined in Organizer’s Guide).
  Provide them a cut down version to reference that covers only their area. They will use this to organize their area’s volunteers.
  Consider delegating the confirmations to the Captains for their areas (e.g., swim: watercraft and volunteer personnel; bike: traffic control; run: aid station needs; Finish: food vendors, announcer).
Finalize and Confirm Venue Setup Needs
  Confirm package pickup location, date, times, setup, and any supporting personnel.
  Contact Administrative personnel overseeing venue area and major event areas to confirm contact information and plans.
  Sufficient garbage containers (including awareness of recycling separation).
  Closure of parking and vehicle access areas as agreed.
  Confirm swim needs.
    Pool: Finalize booked times, access (doors unlocked from staging/to transition), changeroom/showers access, chairs (lap counters).
    Open water: clearance for access for setup on water, placement of turn buoy markers, shutting down beach and open water area.
  Confirm Transition Area Grounds Usage
    Dates and times.
    Automated sprinklers.
    Power outlet availability and working order.
    Grounds closure and lock keys’ access (including early opening of bathroom facilities).
  Bike and run route.
    Closures/restrictions dates and times.
    Traffic control.
Create and Print Site Maps
  Larger format to be posted at package pickup, briefings, and at venue on event days.
  Venue (check in, swim start/exit, transition area, general swim area (start/exit), bike course, run course, finish area, recovery/athlete area, lunch, awards, medical, bike mechanic), Swim (including corrals and warmup)/Bike/Run course, Transition layout.

## Slide 11: Two Weeks Prior
Collaborate Timing Needs
Athletes’ Guide
Confirm Food Vendor Arrangements
Audit Registration Information
Notes: Collaborate on Timing Needs
  Confirm or cancel needs for additional timing chips or other equipment that was tentatively booked.
  Contact remote timer information: name, time zone, email, phone number, availability in week before event date.
  Draw up and agree to timing plan (mat locations, flow across mats for event, race progress and troubleshooting communications, dates and times).
  Agree to results formatting and availability for ranking (medals) and qualifiers. Involve Technical Official’s (TD and Head Referee) to ensure those needs are met.
  Timing personnel may also be able to configure ‘unique’ results for trophies if given time and particulars.
  Note any exceptions for timing results (e.g., under age 12, Try-a-Tri).
  Consider sending preliminary registration file for test load.
Athletes’ Guide
  Finalize and publish online. Include a versioning tag in case (likely) updates are needed.
  Communicate to all.
  Highlight whether there will be an Age Group briefing provided a few days before the event (recorded for streamed viewing).
Confirm Food Vendor Arrangements
  For recovery food and lunches.
  Provide preliminary numbers (should be close by now based on registrations).
  Obtain timing of final order.
  Pickup and delivery.
Audit Registration Information
  If you collect swim times (e.g., pool swim wave interval start), review for anomalies, contact, and correct.

## Slide 12: One Week Prior
Confirm Pickups of Draw Prizes
Confirm Pickups of Outside Equipment
Expect Delivery of Ordered Clothing
Expect Delivery of Race Items
Confirm Photographers
Prepare for Briefings
Notes: Confirm Pickups of Draw Prizes
  In-Kind Sponsors need time to create a box of goodies that can be waiting for pickup.
  You will need time to sort through items to think about distribution at event.
Confirm Pickups of Outside Equipment
  Cargo van/truck.
  Passenger vehicle (for bike/run course).
  Tents, PA system, water jugs with dispensers, backup generators, road signage, barricades, course signage.
Expect Delivery of Ordered Clothing
  Pickup, crosscheck order to received, sort for distribution/athlete packages.
Expect Delivery of Race Items
  Swim caps, wristbands, tattoos, race bibs, race belts, bike numbers, medals, trophies.
  Swag bag and items (e.g., energy bars, coupons). May need to arrange pickup.
Confirm Photographers
  May want to arrange a walkthrough of the event so they can organize.
  Review any restricted areas (including for drones).
Prepare for Briefings
  For Age Group: TD can provide a template PowerPoint to guide the briefing.
    Copy the information from the Organizer’s Guide into the presentation deck.
    Much information in the Athletes’ Guide is repeated in the briefing. However, there are some things not repeated, and there are some things that are said in addition to the Guide. Any changes since the original Athletes’ Guide are also highlighted.
    Work with TD to reserve a day and time to hold the briefing online.
    The AG briefing should be recorded, the recording made available right after the briefing, and the access to the recording communicated right away to all AG registrants.
    Briefing should take a half hour to complete. Additional time can be used to take questions.
    Announce the date and time of the AG briefing (usually in the evening a few days before the event).
    Work with TD to finalize the content in briefing.
  For Elite-style briefing: TD will lead this briefing.
    Ensure the booked room has projector, and sufficient seating for expected racers and coaches. Usually other people are not invited.
    Room should also have a way of controlling access with a check-in desk set up with race packages to be handed to the racers.
    It is expected that the RD will attend and be acknowledged during the briefing.

## Slide 13: Next Sessions: Writing the Event Script
Act 3: Event Week, Day(s) of Event, and Post Event
Notes: This is where it all comes together!
Let the show begin!

## Slide 14
THANKS
FOR YOUR
CONTRIBUTIONS!