## Slide 1: Event Management Course and Workshop
For Triathlon Local Organizing Committees (LOCs)
Facilitators: Terry Hooper & Marlene Hooper
Notes: 1

## Slide 2: Event Management Course and Workshop
For Triathlon Local Organizing Committees (LOCs)
Facilitators: Terry Hooper & Marlene Hooper
Notes: 2

## Slide 3: Course Abstract
Goals
  To increase the knowledge, skills, and capabilities of the individuals and groups involved in managing events.
  To plan, organize, and produce safe, successful events that meet stakeholder needs.
Target
  Community Level, Volunteer Event Organizers Sanctioned by Triathlon Provincial Sport Organization (PSO)
In Scope
  Triathlon PSOs: Alberta, British Columbia, Saskatchewan
  Indoor and Outdoor Swim Events
Attendee Prerequisites
  Event Organizing Experience: None to Moderate
  PTO 1 and 2 ‘Trained’ Status (Preferred)

## Slide 4: Course Content Sources
Triathlon Alberta
Triathlon BC
World Triathlon
Personal Experience

## Slide 5: Course Sessions
Format
  Recorded Video Followed By Live Workshop
Session 1: Setting the Stage
  Expectations and Roles of Various ‘Actors’
Sessions 2 – 4: Writing the Event Script
  Pre-Event, Event Days, Post-Event
  Tasks, Timelines, Checklists
  Address All Actors’ Wants, Needs, Expectations
  Sample Templates and Examples

## Slide 6: Writing the Event Script
Act 1: Ten to Five Months Prior
Act 2: Four Months to One Week Prior
Act 3: Event Week, Day(s) of Event, and Post Event
*The items discussed will be provided in a checklist

## Slide 7: Pre-Event: Seven Days
Send Captains Their Area Information
Review Event Organizers’ Manual
Review Event Checklist
Notes: Send Captains the relevant Organizer's Manual sections (**Show Captain Sample for Check-In**)
  Include pseudo-Captains (e.g., medical: St John Ambulance; Traffic Control; Security; Timing, etc.)
  Confirm ambulance
Review Event Organizer’s Manual
  Determine whether there are any missing items for each of the areas
  Captains can assist with this for their area
Review Event Checklist
  Ensure all items on checklist for final week are identified, scheduled, and assigned

## Slide 8: Pre-Event: Six Days
Purchase Final Race Supplies
Sort Out Packages
Volunteer Assignments
Swim Registration Audit
Facilities Check
Order Food
Notifications to Residents/Businesses
Athletes’ Guide Final Updates
Last Day of Registration Notification
Notes: Purchase final race supplies
  E.g., zip ties, duck tape (check whether TOs will provide mount/dismount), tape for carpet at finish, road marking spray
  Contact timing service and arrange for meeting. Work with TO Head Referee. Confirm timing mat locations and race category configurations (**Show Sample Config**)
  Distribute course notification and information to affected public and businesses
Sort Out Packages
  Could apply to both Participants and Volunteers
  Preparing for distribution of race packages or at race-day check-in
Volunteer Assignments
  Download last set of volunteer registrations
  Allocate volunteers based on preference and need (**Show Sample Sheet of downloads and assignments**)
  Communicate volunteer assignments and Volunteer Guide reference to all Volunteers
  Expect a 10% loss of registered volunteers on responses to emails and on event day
    Be prepared to accept offers at check-in, consider comments with limitations or need to be partnered, consider distribution according to experience
Swim Registration Audit
  Confirm correct kids/youth age groups if you allow racing down an age category. Sometimes age ranges confuse newbies because they don’t understand end-of-year ages and they would rather race in correct age category
  Pool Swim
    Last check of swim times for valid estimated ranges (for wave and start sorting). These should be monitored occasionally with registrations coming in so there are few left to check.
Facilities Check
  Tour swim, bike, run, transition venue area
  Ensure field of play automatic irrigation is turned off
  Ensure all locks will be opened (or gain access to keys) for washrooms and access gates
  Test venue power outlets
    Test all locks with keys and WD40 where necessary
  Confirm availability and/or delivery of garbage/recycle buckets, portable toilets
  Confirm all communications are working – especially cell data for race communications (using data-dependent apps) as well as timing communications via cell data
Order food
  Finalize order to caterer based on current registrations
Notifications to residents/businesses
  Community boxes, home mailboxes (**Show Sample notification**)
Athletes' Guide Final Updates
  Notify via web site, social media, and email distribution
  Any additional updates can be applied, but should also be raised at AG/Elite Briefings at this stage
Last day registration day notification on social media, web site, and email distribution
  Consider how you will handle requests for late registrations
  For Email distribution, use filtering capabilities of platform (**Demo Mailchimp Example with Tags**)

## Slide 9: Pre-Event: Five Days
Packages’ Contents
Timing Service Check-In
Close Registration
Prepare for Registration Reports/Exports
Contact Event Support Groups
Notes: Packages’ Contents
  Obtain Package bags
    Participant and Volunteers (including Technical Officials)
    Consider a retail sponsor that may donate branded bags
  Sponsor brochures
  Any other swag (coupons, energy bars, etc.)
Timing Service Check-In
  Consider sending sample upload file to timing provider using last year’s data.
  Include chip assignment, racer number, first name, last name, team name, gender, results group (e.g., 20-24, duathlon, PSO games qualifier, Just Tri It), start group (duathlon, pool heat/lane/position), commentator info (include city and any comments captured at registration)
  Check resulting reports and information displays. Includes monitoring, medal ranking, trophies, announcer information.
Close Registration
  This milestone is a trigger for many other things. Don’t leave it too late and cause issues!
Prepare for Registration Reports/Exports
  Spreadsheets may be your centralized data store
  Tabs for medical, check-in, swim/run/bike lap counting, etc., random draws, and receiving the results for any special needs not provided with timing configuration (e.g., trophies, qualifier results)
  (**Show Sample Sheet with Tabs for Distribution**)
Contact Event Support Groups
  Hospital notification about event
  Police Watch Commander notification, contact, and provide event emergency contact
  Confirm event medical responder service (e.g., St. John Ambulance)
  Moto leader
  Bike mechanic
    If no mechanic, collect common bike needs: pumps, tubes, tools
    Elite: Supply of neutral, spare wheels
  Overnight Security

## Slide 10: Pre-Event: Four Days
Swim Tasks
Set Racer Information
Race Venue Consumable Provisions
Notes: Swim
  Confirm setup personnel and watercraft, and watercraft for event days. Provide them a schedule.
  Pool Swim
    Work with Swim Captain to sort swimmers into waves, lanes, starts
    Add cap colour, lap count checkboxes
Set racer information
  Begin assignment of racer number (sync with available bib numbers)
  Once racer information is locked in, send registrant file to timing
  As has been done with Timing test file, include chip assignment, racer number, first name, last name, team name, gender, results group (e.g., 20-24, duathlon, PSO games qualifier, Just Tri It), start group (duathlon, pool heat/lane/position), commentator info (include city and any comments captured at registration)
    Ensure a pool swim with interval lane starts are properly allocated to waves to sync with start.
  (**Show Sample Sheet with Tabs for Distribution**)
Race venue consumable provisions
  Tim Hortons coffee order for Sunday morning
  Costco: paper plates, napkins
  Print large format maps
  5 gal water bottles, water flats
  Air horn (for start), felt pens (numbering athletes)
  Any other goodies?

## Slide 11: Pre-Event: Three Days
Traffic Messaging for Bike
Photography
Stuff Athlete Packages
Stuff Volunteer Packages
Captains Communications
Age Group Briefing (Online)
Notes: Traffic Messaging for Bike
  Traffic Control Message Boards set up
Photography
  Check with personnel with schedule and locations (potentially include package pickup)
Stuff Athlete Packages
  Print stuffing list
  Separate into ‘guaranteed order cutoff’ versus ‘first come first serve sizes if they’re available’
  Racer bibs
  Print labels: bike (Racer #) and package (first name, racer #) (**Show Sample Word Doc Mail Merge**)
Stuff Volunteer Packages
  Include all items that are general distribution
  Don’t include t-shirts
Captains Communications
  Distribute current area volunteer list
  Notify Captains of final registration numbers
  Print run sheets for captains and put in plastic sleeves with lanyards
Age Group Briefing (Online)
  Conduct briefing in collaboration with Technical Delegate
  Have briefing streamed online and recorded, posting recording right away, and then promoting it for participants through the web site, social media, and email distribution.

## Slide 12: Pre-Event: Two Days
Get Transport Truck or Trailer
Prepare Transport for Package Pickup
Final Timing Check
Print Event Documents
Notes: Get transport truck or trailer
  Pick up all sponsor-branded pop-up tents, tables, and another other sponsor donations
  Pick up generator
  Public Address System: Pick up for announcer
Prepare transport for package pickup
  Participant packages
  Printed registrant reports
  Print schedule, maps and lists for posting at package pickup, and then posting later in check-in area
Final Timing Check
  Confirm all data is loaded and reports are ready
  Ensure all equipment is ready: chips tested and labels verified, readers charged, loops packed, cell data devices charged with apps up to date
  Timing plan has been reviewed
  Stopwatches (manual backup): battery levels acceptable, watches synchronized
  Ensure Head Referee Technical Official has coordinated with Timing for needs and interactions
Print Event Documents
  Lap counter sheets for swim, bike, run
  Manual timing sheets
  First aid participant information
  Announcer notes (in case of electronic issues)
  Check-in by racer number and name
  Volunteer assignments
  Start lists for all captains
  Transition race labels

## Slide 13: Pre-Event: Last Day
Package Pickup
Conduct Orientation
Set up Transition
  Bike Check-In
Set up Open Water Swim
Prepare Bike and Run Routes
Elite Briefing
Notes: Package Pickup
  Set up stations: reception, package distribution
    Reception could have slips of peoples’ names to take for package distribution
  Post venue and course maps, and schedules in separate area
  Computer with access to registration information
Conduct Orientation
  Held at venue
  Scheduled to provide to participants and volunteers
Set up Transition
  AG:
    Racks five metres apart with spacing between racks and fence of five metres
    Three metre rack would have three bikes on each side.
    Signs posted on racks to guide athletes to correct area. Optional to put racer numbers on rack positions
  Elite
    Racks six metres apart
    Name plates for each athlete
    Separate men and women space blocks
    Have three bikes on one side of each rack
    Bucket for each spot
  Fencing enclosure with closing entry/exits
Bike Check-In
  Can have bikes placed in transition day before event to reduce load on event morning
  Transition would be set up in advance
  Involve Technical Officials for equipment check
Set up Open Water Swim
  Course Setup with marker buoys left for next morning
  Support TOs: Swim: Preliminary Water Temperature (for Elite Briefing), course(s) distance measurements check (laser rangefinder)
  Swim Course Familiarization (includes safety support)
Prepare Bike and Run Routes
  Streets (corners) sweep and mark cycling and run hazards. Consider prearranging street sweeper with city or road maintenance in week leading up to event
  Note serious issues for Elite Briefing
Elite Briefing
  Conducted in late afternoon or very early evening
  Briefing registration
  Doors closed at briefing start time and late athletes recorded
  Lead by Technical Delegate in closed room with chairs, with large screen TVs, or projector and projection screen.. Race Director is encouraged to attend
  Packages distributed after meeting

## Slide 14: Event Day – It’s Showtime!
Deploy as Agreed with Technical Delegate
Official Results
Scan/File All Event Logging Documents
Notes: Deploy as agreed with Technical Delegate
  Event configuration and schedule
Official Results
  TO Head Referee to review and signoff on timing
Scan/file all event logging documents
  For timing audit and correction
  Pool Swim: Scan lap count sheets
  Lap count sheets
  Manual timing sheets

## Slide 15: Epilogue: Week One
Return All Equipment
Retrieve Notices
Post Official Results
Lost and Found
Upload Photos
Feedback
Organize Volunteer Appreciation
PSO Follow-Up Reports
Notes: Return all equipment
  Pop up Tents
  PA system to Long & McQuade
  Generator
  Return transport van/truck
  Return all loaned keys
Retrieve notices posted to residents and businesses
Post official results
  Ranking, trophies
  Web site with notice on social media and email distribution
  Post results to local papers
  Submit qualifier results
Lost and found
  Collect, photograph, and issue notice on social media and email distribution (participants and volunteers)
Upload Photos
  Collect all photos and publish to a publicly-accessible online location (participants and volunteers)
  Post access method on web site
Feedback
  Participant and volunteer post-event surveys with one-week response deadline (**Show Survey Samples for Participant and Volunteer**)
Organize Volunteer Appreciation
  Hold a volunteer get-together event. Share photos
PSO Follow-up Reports
Bundle Information
  Participants: Results, Lost and Found, Photos, Survey
  Volunteers: Lost and Found, Photos, Survey, Volunteer Appreciation Info

## Slide 16: Epilogue: Week Two
Finalize Financials
Submit Grant Reporting
Compile Survey Results
Letter of Thanks
Engrave Trophies
Inventory
Arrange Meeting with Technical Delegate
Notes: Finalize financials
  Have actuals versus budget
  Payments to vendors and volunteers for expenses
Submit grant reporting requirements
Compile survey results
Letters of Thanks
  Satisfy any sponsor post-event obligations (e.g., social media posts)
  Send email to sponsors with event participation stats and survey summary. Include photos of sponsor branding.
  Thank partners (i.e., Traffic Control, RCMP, First Aid Responders/St. John Ambulance, photographers, security, ambulance)
Engrave Trophies
  If trophies aren’t displayed, consider loaning trophies to recipients
Inventory
  Race equipment and consumables with location
Arrange Meeting with Technical Delegate

## Slide 17: Repeat Engagement
File Documents
Create Next Year Folder
Reuse Materials to Accelerate Next Year’s Event Planning

## Slide 18
THANKS
FOR YOUR
CONTRIBUTIONS!